## Wave 19f
Migration Wave | Target Destination | Datacenter-Dataroom | Country | City | Hostname | Status | Application | Environment | Source IP | Target IP | Primary Target IP | FQDN | Macro OS | DB Type | Layer | Datastore Target | Destination | Backup Type | Backup Scheduled Hour | Backup Frequency | Date First backup on Commvault | Hour _ First Backup on Commvault | Focal Point Application | Mail Contact
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV040B | Migrato | DOCUMENTUM | Prod | '10.128.176.195 | - | - | sasv040b.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 19:10 | 24Hrs |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV01ME | Migrato | CENTERSTAGE | Prod | '10.129.155.83 | - | - | SASV01ME.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 19:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV01PM | Migrato | CENTERSTAGE | Prod | '10.129.155.19 | - | - | SASV01PM.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 2:40 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030R | Migrato | CENTERSTAGE | Prod | '10.129.155.93 | - | - | SASV030R.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030S | Migrato | CENTERSTAGE | Prod | '10.129.155.122 | - | - | SASV030S.saipemnet.saipem.intranet | Windows Server | Oracle | DB | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030T | Migrato | CENTERSTAGE | Prod | '10.129.142.215 | - | - | SASV030T.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM4 | FS\RMAN\Arch | 2:30\5:00\11:00 | Full Everyday\Full Everyday\Full Everyday |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03FF | Migrato | CENTERSTAGE | Prod | '10.128.190.168 | - | - | SASV03FF.saipemnet.saipem.intranet | Windows Server | Oracle | DB | ACN-AMS-DS-PR** | AM6 | VBA | 5:15 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV028Q | Migrato | CENTERSTAGE | Prod | '10.128.177.113 | - | - | SASV028Q.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02M8 | Migrato | CENTERSTAGE | Prod | '10.128.176.73 | - | - | SASV02M8.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02M9 | Migrato | CENTERSTAGE | Prod | '10.128.176.72 | - | - | SASV02M9.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MA | Migrato | CENTERSTAGE | Prod | '10.128.176.71 | - | - | SASV02MA.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 23:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MB | Migrato | CENTERSTAGE | Prod | '10.128.176.70 | - | - | SASV02MB.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MF | Migrato | CENTERSTAGE | Prod | '10.128.176.66 | - | - | SASV02MF.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0308 | Migrato | CENTERSTAGE | Prod | '10.129.155.105 | - | - | SASV0308.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03EO | Migrato | CENTERSTAGE | Prod | '10.128.191.0 | - | - | SASV03EO.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03HN | Migrato | CENTERSTAGE | Prod | '10.128.190.148 | - | - | SASV03HN.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02CZ | Migrato | D2-xCP | Prod | '10.131.167.22 | - | - | SASV02CZ.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 23:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02D0 | Migrato | D2-xCP | Prod | '10.131.167.23 | - | - | SASV02D0.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02D4 | Migrato | D2-xCP | Prod | '10.128.176.251 | - | - | SASV02D4.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM6 | FS\RMAN\Arch | 0:00\21:00\2:00 | Weekly Full+Daily Incr\Weekly Full+Daily Incr\Full Everyday |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV035O | Migrato | D2-xCP | Prod | '10.128.176.4 | - | - | SASV035O.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 4:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV035P | Migrato | D2-xCP | Prod | '10.128.176.5 | - | - | SASV035P.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 1:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03BU | Migrato | D2-xCP | Prod | '10.128.191.217 | - | - | SASV03BU.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03BV | Migrato | D2-xCP | Prod | '10.128.191.226 | - | - | SASV03BV.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 3:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03T3 | Migrato | D2-xCP | Prod | '10.129.154.102 | - | - | SASV03T3.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 5:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03T4 | Migrato | D2-xCP | Prod | '10.129.154.104 | - | - | SASV03T4.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 5:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03T5 | Migrato | D2-xCP | Prod | '10.129.154.110 | - | - | SASV03T5.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 7:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03T6 | Migrato | D2-xCP | Prod | '10.129.154.134 | - | - | SASV03T6.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 7:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03T7 | Migrato | D2-xCP | Prod | '10.129.154.154 | - | - | SASV03T7.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 3:10 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02TU | Migrato | D2-xCP | Prod | '10.128.191.209 | - | - | SASV02TU.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | FS | 22:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZI | Migrato | D2-xCP | Prod | '10.128.177.197 | - | - | SASV02ZI.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0308 | Migrato | D2-xCP | Prod | '10.129.155.105 | - | - | SASV0308.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0309 | Migrato | D2-xCP | Prod | '10.129.155.221 | - | - | SASV0309.saipemnet.saipem.intranet | Linux | -- | AS | ACN-AMS-DS-PR** | AM6 | FS | 21:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030A | Migrato | D2-xCP | Prod | '10.129.155.243 | - | - | SASV030A.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030B | Migrato | D2-xCP | Prod | '10.129.155.246 | - | - | SASV030B.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03EO | Migrato | D2-xCP | Prod | '10.128.191.0 | - | - | SASV03EO.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03F5 | Migrato | D2-xCP | Prod | '10.128.190.181 | - | - | SASV03F5.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 1:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03F6 | Migrato | D2-xCP | Prod | '10.128.190.182 | - | - | SASV03F6.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | FS/VBA | 1:30/6:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03FV | Migrato | D2-xCP | Prod | '10.128.190.162 | - | - | SASV03FV.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AM6-PR-DS** | AM6 | VBA | 21:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03FW | Migrato | D2-xCP | Prod | '10.128.190.161 | - | - | SASV03FW.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AM6-PR-DS** | AM6 | VBA | 21:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03HN | Migrato | D2-xCP | Prod | '10.128.190.148 | - | - | SASV03HN.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03KY | Migrato | D2-xCP | Prod | '10.128.190.88 | - | - | SASV03KY.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV043B | Migrato | D2-xCP | Prod | '10.129.77.120 | - | - | sasv043b.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 0:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV028Q | Migrato | DAMS | Prod | '10.128.177.113 | - | - | SASV028Q.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02M8 | Migrato | DAMS | Prod | '10.128.176.73 | - | - | SASV02M8.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02M9 | Migrato | DAMS | Prod | '10.128.176.72 | - | - | SASV02M9.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MA | Migrato | DAMS | Prod | '10.128.176.71 | - | - | SASV02MA.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 23:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MB | Migrato | DAMS | Prod | '10.128.176.70 | - | - | SASV02MB.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV017H | Migrato | DAMS | Prod | '10.131.157.86 | - | - | SASV017H.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 18:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV017I | Migrato | DAMS | Prod | '10.131.157.87 | - | - | SASV017I.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 2:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV01A6 | Migrato | DAMS | Prod | '10.129.155.193 | - | - | SASV01A6.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 22:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MF | Migrato | DAMS | Prod | '10.128.176.66 | - | - | SASV02MF.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03F3 | Migrato | DAMS | Prod | '10.128.190.183 | - | - | SASV03F3.saipemnet.saipem.intranet | Windows Server | Oracle | DB | ACN-AMS-DS-PR** | AM6 | VBA | 1:10 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0308 | Migrato | DAMS | Prod | '10.129.155.105 | - | - | SASV0308.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03KM | Migrato | DAMS | Prod | '10.128.190.255 | - | - | SASV03KM.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03KT | Migrato | DAMS | Prod | '10.128.190.93 | - | - | SASV03KT.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 3:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03NB | Migrato | DAMS | Prod | '10.129.142.143 | - | - | SASV03NB.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM6 | FS/RMAN/ARCH | 19:00/6:00/0:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03EO | Migrato | DAMS | Prod | '10.128.191.0 | - | - | SASV03EO.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03F5 | Migrato | DAMS | Prod | '10.128.190.181 | - | - | SASV03F5.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 1:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03F6 | Migrato | DAMS | Prod | '10.128.190.182 | - | - | SASV03F6.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | FS/VBA | 1:30/6:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03FV | Migrato | DAMS | Prod | '10.128.190.162 | - | - | SASV03FV.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AM6-PR-DS** | AM6 | VBA | 21:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03FW | Migrato | DAMS | Prod | '10.128.190.161 | - | - | SASV03FW.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AM6-PR-DS** | AM6 | VBA | 21:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03HN | Migrato | DAMS | Prod | '10.128.190.148 | - | - | SASV03HN.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SAWS034P | Migrato | DAMS | Prod | '10.129.155.102 | - | - | SAWS034P.saipemnet.saipem.intranet | Windows client | -- | WS | ACN-AMS-DS-PR** | AM6 | VBA | 3:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02M9 | Migrato | GLOBAL REGISTRY | Prod | '10.128.176.72 | - | - | SASV02M9.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 22:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02MF | Migrato | GLOBAL REGISTRY | Prod | '10.128.176.66 | - | - | SASV02MF.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:30 | Daily Incr |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030A | Migrato | GLOBAL REGISTRY | Prod | '10.129.155.243 | - | - | SASV030A.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030B | Migrato | GLOBAL REGISTRY | Prod | '10.129.155.246 | - | - | SASV030B.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02TU | Migrato | PAGE | Prod | '10.128.191.209 | - | - | SASV02TU.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | FS | 22:00 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZI | Migrato | PAGE | Prod | '10.128.177.197 | - | - | SASV02ZI.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0308 | Migrato | PAGE | Prod | '10.129.155.105 | - | - | SASV0308.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | Daily Incr |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0309 | Migrato | PAGE | Prod | '10.129.155.221 | - | - | SASV0309.saipemnet.saipem.intranet | Linux | -- | AS | ACN-AMS-DS-PR** | AM6 | FS | 21:00 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030A | Migrato | PAGE | Prod | '10.129.155.243 | - | - | SASV030A.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV030B | Migrato | PAGE | Prod | '10.129.155.246 | - | - | SASV030B.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:00 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02YM | Migrato | PAGE | Prod | '10.129.142.223 | - | - | SASV02YM.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM4 | FS\RMAN ARCH\FULL | 1:00\2:00\21:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02Z7 | Migrato | PAGE | Prod | '10.128.176.80 | - | - | SASV02Z7.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 21:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02Z8 | Migrato | PAGE | Prod | '10.128.176.81 | - | - | SASV02Z8.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 21:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02Z9 | Migrato | PAGE | Prod | '10.128.176.177 | - | - | SASV02Z9.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 23:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZA | Migrato | PAGE | Prod | '10.128.176.180 | - | - | SASV02ZA.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZB | Migrato | PAGE | Prod | '10.128.176.181 | - | - | SASV02ZB.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 22:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZC | Migrato | PAGE | Prod | '10.128.176.182 | - | - | SASV02ZC.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 22:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZD | Migrato | PAGE | Prod | '10.128.176.254 | - | - | SASV02ZD.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZE | Migrato | PAGE | Prod | '10.128.176.255 | - | - | SASV02ZE.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZF | Migrato | PAGE | Prod | '10.128.177.182 | - | - | SASV02ZF.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 2:40 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZG | Migrato | PAGE | Prod | '10.128.177.183 | - | - | SASV02ZG.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 2:40 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02ZH | Migrato | PAGE | Prod | '10.128.177.196 | - | - | SASV02ZH.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0304 | Migrato | PAGE | Prod | '10.129.154.122 | - | - | SASV0304.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0305 | Migrato | PAGE | Prod | '10.129.154.193 | - | - | SASV0305.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM6-PR-DS** | AM6 | VBA | 6:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0306 | Migrato | PAGE | Prod | '10.129.154.155 | - | - | SASV0306.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0307 | Migrato | PAGE | Prod | '10.129.155.91 | - | - | SASV0307.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AM4-PR-DS** | AM4 | VBA | 21:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV031U | Migrato | PAGE | Prod | '10.129.142.212 | - | - | SASV031U.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM4 | FS | 1:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV034C | Migrato | PAGE | Prod | '10.129.155.142 | - | - | SASV034C.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 21:20 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0395 | Migrato | PAGE | Prod | '10.128.191.31 | - | - | SASV0395.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 6:15 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0396 | Migrato | PAGE | Prod | '10.128.191.30 | - | - | SASV0396.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 6:00 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0397 | Migrato | PAGE | Prod | '10.128.191.27 | - | - | SASV0397.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:20 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV0398 | Migrato | PAGE | Prod | '10.128.191.28 | - | - | SASV0398.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 1:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03EO | Migrato | PAGE | Prod | '10.128.191.0 | - | - | SASV03EO.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Daily Incr |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03ZU | Migrato | PAGE | Prod | '10.128.191.241 | - | - | sasv03zu.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 0:30 | 24Hrs |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV043B | Migrato | PAGE | Prod | '10.129.77.120 | - | - | sasv043b.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM4 | VBA | 0:00 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03HN | Migrato | PAGE | Prod | '10.128.190.148 | - | - | SASV03HN.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Daily Incr |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03KY | Migrato | PAGE | Prod | '10.128.190.88 | - | - | SASV03KY.saipemnet.saipem.intranet | Windows Server | -- | FE | ACN-AMS-DS-PR** | AM6 | VBA | 4:50 | Every Day |  |  | Cerrai Guido | Guido.Cerrai@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV02D4 | Migrato | TRIBEFIRE | Prod | '10.128.176.251 | - | - | SASV02D4.saipemnet.saipem.intranet | Linux | Oracle | DB | ACN-AMS-DS-PR** | AM6 | FS\RMAN\Arch | 0:00\21:00\2:00 | Weekly Full+Daily Incr\Weekly Full+Daily Incr\Full Everyday |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03BV | Migrato | TRIBEFIRE | Prod | '10.128.191.226 | - | - | SASV03BV.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM4 | VBA | 3:00 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Wave F | Private Cloud (AMS CNF) | Datacenter | Italy | San Donato Milanese | SASV03BU | Migrato | TRIBEFIRE | Prod | '10.128.191.217 | - | - | SASV03BU.saipemnet.saipem.intranet | Windows Server | -- | AS | ACN-AMS-DS-PR** | AM6 | VBA | 4:30 | Every Day |  |  | Verdecchia Marco | Marco.Verdecchia@saipem.com;
Note on H1: Amero, Alda: in rosso le applicazioni che sono in ambito compliance 262